## We need a Gantt chart for this
Project Title | PULCASH: LAUNCH OF DIGITAL BANKING IN AZERBAIJAN | [21 empty] | Company name | Pulcash
Project Manager and CEO | Rovshan Ahmadov | [21 empty] | Date | 2024-04-01
Week
Task | Start Date | End Date | Duration (Weeks) | Progress |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
Project Initiation
Define Project Scope & Goals | 2023-12-01 | 2023-12-15 | 2 | 100% | bar: 1 to 2
Secure Funding & Investment | 2023-12-01 | 2024-01-31 | 8 | 60% | bar: 1 to 8
Product Development
Design User Interface (UI) & User Experience (UX) | 2024-01-15 | 2024-03-15 | 8 | 65% | bar: 1 to 8
Develop Core Banking System Features | 2024-02-01 | 2024-05-31 | 16 | 85%
Integrate Payment Gateways | 2024-03-15 | 2024-04-30 | 6 | 75% | bar: 1 to 6
Develop Mobile App | 2024-02-15 | 2024-05-31 | 16 | 50%
Implement Security Measures | 2024-04-01 | 2024-05-31 | 8 | 75% | bar: 1 to 8
Testing & Refinement
Internal Alpha Testing | 2024-06-03 | 2024-06-21 | 2.5714 | 60% | bar: 1 to 3
Beta Testing with Limited Users | 2024-06-24 | 2024-07-19 | 3.5714 | 60% | bar: 1 to 4
Bug fixing and Refinements | 2024-07-22 | 2024-08-09 | 2.5714 | 75% | bar: 1 to 3
Marketing & User Acquisition
Develop Marketing Strategy | 2024-01-15 | 2024-02-29 | 6.4286 | 90% | bar: 1 to 6
Design Marketing Materials & Campaigns | 2024-03-01 | 2024-05-31 | 12 | 85% | bar: 1 to 12
Launch Pre-Registration Campaign | 2024-05-15 | 2024-06-30 | 6 | 80% | bar: 1 to 6
Launch & Go-Live
Final System Testing & Integration | 2024-08-12 | 2024-09-06 | 3.5714 | 30% | bar: 1 to 4
Beta Testing Final Release | 2024-09-09 | 2024-10-09 | 4.2857 | 30% | bar: 1 to 4
Official Launch of Pulcash Mobile App | 2024-12-11 | 2024-12-11 | 0 | 0%
Post-Launch & Growth
Monitor System Performance & User Feedback | 2024-12-16 | Ongoing | Ongoing | 0%
Implement New Features & Functionality | 2024-12-16 | Ongoing | Ongoing | 0%
Customer Support & Onboarding | 2024-12-16 | Ongoing | Ongoing | 0%